## Effort & Cost
| Task Name | Task code | PM Team | Design Team | Purchasing Team | Development Team | Test Team
WP0 | Project Management | 0.1 | 68
WP1 | Content design | 1.1 |  | 3
| Client functionalities design | 1.2 |  | 3
| Client - server design | 1.3 |  | 7
| DB Design | 1.4 |  | 10
| SW technical design | 1.5 |  | 63
WP2 | Client sw vendor selection | 2.1 |  |  | 1
| Vendor negotiation | 2.2 |  |  | 1
WP3 | Client development | 3.1 |  |  |  | 15
| DB development | 3.2 |  |  |  | 18
| Client configuration | 3.3 |  |  |  | 9
| SW internal development | 3.4 |  |  |  | 33
| Client final version release | 3.5 |  |  |  | 24
WP4 | DB robustness test | 4.1 |  |  |  |  | 2
| Customer version release | 4.2 |  |  |  |  | 4
| Customer test | 4.3 |  |  |  |  | 6
| Final robustness test | 4.4 |  |  |  |  | 4
| Task Name | Task code | PM Team | Design Team | Purchasing Team | Development Team | Test Team | Costi personale | Costi trasferta | Costi acquisto | Costi totali
WP0 | Project Management | 0.1 | 68000 | 0 | 0 | 0 | 0 | 68000 | 10000 |  | 78000
WP1 | Content design | 1.1 | 0 | 3000 | 0 | 0 | 0 | 3000 |  |  | 3000
| Client functionalities design | 1.2 | 0 | 3000 | 0 | 0 | 0 | 3000 |  |  | 3000
| Client - server design | 1.3 | 0 | 7000 | 0 | 0 | 0 | 7000 |  |  | 7000
| DB Design | 1.4 | 0 | 10000 | 0 | 0 | 0 | 10000 |  |  | 10000
| SW technical design | 1.5 | 0 | 63000 | 0 | 0 | 0 | 63000 |  |  | 63000
WP2 | Client sw vendor selection | 2.1 | 0 | 0 | 1000 | 0 | 0 | 1000 | 5000 |  | 6000
| Vendor negotiation | 2.2 | 0 | 0 | 1000 | 0 | 0 | 1000 |  | 50000 | 51000
WP3 | Client development | 3.1 | 0 | 0 | 0 | 15000 | 0 | 15000 |  |  | 15000
| DB development | 3.2 | 0 | 0 | 0 | 18000 | 0 | 18000 |  |  | 18000
| Client configuration | 3.3 | 0 | 0 | 0 | 9000 | 0 | 9000 |  |  | 9000
| SW internal development | 3.4 | 0 | 0 | 0 | 33000 | 0 | 33000 |  |  | 33000
| Client final version release | 3.5 | 0 | 0 | 0 | 24000 | 0 | 24000 |  |  | 24000
WP4 | DB robustness test | 4.1 | 0 | 0 | 0 | 0 | 2000 | 2000 |  |  | 2000
| Customer version release | 4.2 | 0 | 0 | 0 | 0 | 4000 | 4000 |  |  | 4000
| Customer test | 4.3 | 0 | 0 | 0 | 0 | 6000 | 6000 | 5000 |  | 11000
| Final robustness test | 4.4 | 0 | 0 | 0 | 0 | 4000 | 4000 |  |  | 4000
[8 empty] | 271000 | 20000 | 50000 | 341000
| Costo medio personale | 1000
| Costi totali | 341000
| Management Reserve | 10230
| Budget | 351230
| Offerta | 413211.7647
| Margine | 61981.7647

## Network
|  | 15 | 25 |  | 25 | 31 |  | 31 | 32
|  | 1.4 (10) |  |  | 3.2 (6) |  |  | 4.1 (1)
6 | 15 | 9 | 19 |  | 19 | 25 |  | 25 | 26
1.1 (9)
0 | 9
|  |  | 3 | 24
1.5 (21)
[10 empty] | 24 | 32 | 32 | 34
|  |  | 3 | 24 | [5 empty] | 3.5 (8) |  | 4.4 (2)
0 | 3
1.2 (3) |  |  | 23 | 24 | [5 empty] | 24 | 32 | 32 | 34
2.1 (1)
0 | 3
|  |  | 3 | 4
|  |  | 13 | 14
2.2 (1)
|  |  | 3 | 4
[10 empty] | 21 | 24
7 | 14 | [8 empty] | 3.3 (3)
1.3 (7) | [6 empty] | 14 | 19
[7 empty] | 3.1 (5) |  |  | 12 | 15
0 | 7 | [10 empty] | 30 | 32
[7 empty] | 7 | 12 |  |  |  | 4.2 (2)
[10 empty] | 19 | 30
[10 empty] | 3.4 (11) |  | 23 | 25
[10 empty] | 12 | 23 | 31 | 34
4.3 (3)
[12 empty] | 23 | 26

## PERT ALAP
|  |  |  | Durate | [13 empty] | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39
| Task Name | Task code | Predec. | Ottimistica | Media | Pessimistica | Attesa | Durata | Predec. | V | σ | Dmi | Dmf | DMi | DMf | RT | Costo
WP0 | Project Management | 0.1 | - | - | - | - | - | 34 | - | 0 | 0 | 0 | 34 | 0 | 34 | 0 | 78000 | 2294.1176 | 2294.1176 | 2294.1176 | 2294.1176 | 2294.1176 | 2294.1176 | 2294.1176 | 2294.1176 | 2294.1176 | 2294.1176 | 2294.1176 | 2294.1176 | 2294.1176 | 2294.1176 | 2294.1176 | 2294.1176 | 2294.1176 | 2294.1176 | 2294.1176 | 2294.1176 | 2294.1176 | 2294.1176 | 2294.1176 | 2294.1176 | 2294.1176 | 2294.1176 | 2294.1176 | 2294.1176 | 2294.1176 | 2294.1176 | 2294.1176 | 2294.1176 | 2294.1176 | 2294.1176
WP1 | Content design | 1.1 | - | 6 | 9 | 12 | 9 | 9 | - | 1 | 1 | 0 | 9 | 6 | 15 | 6 | 3000 | 6: 333.3333; 7: 333.3333; 8: 333.3333; 9: 333.3333; 10: 333.3333; 11: 333.3333; 12: 333.3333; 13: 333.3333; 14: 333.3333
| Client functionalities design | 1.2 | - | 1 | 3 | 5 | 3 | 3 | - | 0.44444 | 0.66667 | 0 | 3 | 0 | 3 | 0 | 3000 | 0: 1000; 1: 1000; 2: 1000
| Client - server design | 1.3 | - | 1 | 8 | 9 | 7 | 7 | - | 1.7778 | 1.3333 | 0 | 7 | 7 | 14 | 7 | 7000 | 7: 1000; 8: 1000; 9: 1000; 10: 1000; 11: 1000; 12: 1000; 13: 1000
| DB Design | 1.4 | 1.1 | 4 | 6 | 32 | 10 | 10 | 1.1 | 21.7778 | 4.6667 | 9 | 19 | 15 | 25 | 6 | 10000 | 15: 1000; 16: 1000; 17: 1000; 18: 1000; 19: 1000; 20: 1000; 21: 1000; 22: 1000; 23: 1000; 24: 1000
| SW technical design | 1.5 | 1.2 | 10 | 22 | 28 | 21 | 21 | 1.2 | 9 | 3 | 3 | 24 | 3 | 24 | 0 | 63000 | 3: 3000; 4: 3000; 5: 3000; 6: 3000; 7: 3000; 8: 3000; 9: 3000; 10: 3000; 11: 3000; 12: 3000; 13: 3000; 14: 3000; 15: 3000; 16: 3000; 17: 3000; 18: 3000; 19: 3000; 20: 3000; 21: 3000; 22: 3000; 23: 3000
WP2 | Client sw vendor selection | 2.1 | 1.2 | 1 | 1 | 1 | 1 | 1 | 1.2 | 0 | 0 | 3 | 4 | 23 | 24 | 20 | 6000 | 23: 6000
| Vendor negotiation | 2.2 | 1.2 | 1 | 1 | 1 | 1 | 1 | 1.2 | 0 | 0 | 3 | 4 | 13 | 14 | 10 | 51000 | 13: 51000
WP3 | Client development | 3.1 | 1.3, 2.2 | 2 | 4 | 12 | 5 | 5 | 1.3, 2.2 | 2.7778 | 1.6667 | 7 | 12 | 14 | 19 | 7 | 15000 | 14: 3000; 15: 3000; 16: 3000; 17: 3000; 18: 3000
| DB development | 3.2 | 1.4 | 5 | 6 | 7 | 6 | 6 | 1.4 | 0.11111 | 0.33333 | 19 | 25 | 25 | 31 | 6 | 18000 | 25: 3000; 26: 3000; 27: 3000; 28: 3000; 29: 3000; 30: 3000
| Client configuration | 3.3 | 3.1 | 1 | 3 | 5 | 3 | 3 | 3.1 | 0.44444 | 0.66667 | 12 | 15 | 21 | 24 | 9 | 9000 | 21: 3000; 22: 3000; 23: 3000
| SW internal development | 3.4 | 3.1 | 4 | 12 | 14 | 11 | 11 | 3.1 | 2.7778 | 1.6667 | 12 | 23 | 19 | 30 | 7 | 33000 | 19: 3000; 20: 3000; 21: 3000; 22: 3000; 23: 3000; 24: 3000; 25: 3000; 26: 3000; 27: 3000; 28: 3000; 29: 3000
| Client final version release | 3.5 | 2.1, 1.5, 3.3 | 8 | 8 | 8 | 8 | 8 | 2.1, 1.5, 3.3 | 0 | 0 | 24 | 32 | 24 | 32 | 0 | 24000 | 24: 3000; 25: 3000; 26: 3000; 27: 3000; 28: 3000; 29: 3000; 30: 3000; 31: 3000
WP4 | DB robustness test | 4.1 | 3.2 | 1 | 1 | 1 | 1 | 1 | 3.2 | 0 | 0 | 25 | 26 | 31 | 32 | 6 | 2000 | 31: 2000
| Customer version release | 4.2 | 3.4 | 2 | 2 | 2 | 2 | 2 | 3.4 | 0 | 0 | 23 | 25 | 30 | 32 | 7 | 4000 | 30: 2000; 31: 2000
| Customer test | 4.3 | 3.4 | 1 | 3 | 5 | 3 | 3 | 3.4 | 0.44444 | 0.66667 | 23 | 26 | 31 | 34 | 8 | 11000 | 31: 3666.6667; 32: 3666.6667; 33: 3666.6667
| Final robustness test | 4.4 | 3.5, 4.1, 4.2 | 2 | 2 | 2 | 2 | 2 | 3.5, 4.1, 4.2 | 0 | 0 | 32 | 34 | 32 | 34 | 0 | 4000 | 32: 2000; 33: 2000
[17 empty] | 341000 | 3294.1176 | 3294.1176 | 3294.1176 | 5294.1176 | 5294.1176 | 5294.1176 | 5627.451 | 6627.451 | 6627.451 | 6627.451 | 6627.451 | 6627.451 | 6627.451 | 57627.451 | 8627.451 | 9294.1176 | 9294.1176 | 9294.1176 | 9294.1176 | 9294.1176 | 9294.1176 | 12294.1176 | 12294.1176 | 18294.1176 | 9294.1176 | 11294.1176 | 11294.1176 | 11294.1176 | 11294.1176 | 11294.1176 | 10294.1176 | 12960.7843 | 7960.7843 | 7960.7843
| Tempo atteso | 34 | [15 empty] | 3294.1176 | 6588.2353 | 9882.3529 | 15176.4706 | 20470.5882 | 25764.7059 | 31392.1569 | 38019.6078 | 44647.0588 | 51274.5098 | 57901.9608 | 64529.4118 | 71156.8627 | 128784.3137 | 137411.7647 | 146705.8824 | 156000 | 165294.1176 | 174588.2353 | 183882.3529 | 193176.4706 | 205470.5882 | 217764.7059 | 236058.8235 | 245352.9412 | 256647.0588 | 267941.1765 | 279235.2941 | 290529.4118 | 301823.5294 | 312117.6471 | 325078.4314 | 333039.2157 | 341000
| Durata promessa al cliente | 36
| σ | 3.0732
| Z | 0.65079
| Probabilità completamento in tempo | 74.22%

## Piano SAL
[9 empty] | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39
Task | Durata | Predec. | Dmi | Dmf | DMi | DMf | RT | Costo
0.1 | 34 | - | 0 | - | - | - | - | 78000 | 2294.1176 | 2294.1176 | 2294.1176 | 2294.1176 | 2294.1176 | 2294.1176 | 2294.1176 | 2294.1176 | 2294.1176 | 2294.1176 | 2294.1176 | 2294.1176 | 2294.1176 | 2294.1176 | 2294.1176 | 2294.1176 | 2294.1176 | 2294.1176 | 2294.1176 | 2294.1176 | 2294.1176 | 2294.1176 | 2294.1176 | 2294.1176 | 2294.1176 | 2294.1176 | 2294.1176 | 2294.1176 | 2294.1176 | 2294.1176 | 2294.1176 | 2294.1176 | 2294.1176 | 2294.1176
1.1 | 9 | - | 0 | 9 | 6 | 15 | 6 | 3000 | 6: 333.3333; 7: 333.3333; 8: 333.3333; 9: 333.3333; 10: 333.3333; 11: 333.3333; 12: 333.3333; 13: 333.3333; 14: 333.3333
1.2 | 3 | - | 0 | 3 | 0 | 3 | 0 | 3000 | 0: 1000; 1: 1000; 2: 1000
1.3 | 7 | - | 0 | 7 | 7 | 14 | 7 | 7000 | 0: 1000; 1: 1000; 2: 1000; 3: 1000; 4: 1000; 5: 1000; 6: 1000
1.4 | 10 | 1.1 | 9 | 19 | 15 | 25 | 6 | 10000 | 15: 1000; 16: 1000; 17: 1000; 18: 1000; 19: 1000; 20: 1000; 21: 1000; 22: 1000; 23: 1000; 24: 1000
1.5 | 21 | 1.2 | 3 | 24 | 3 | 24 | 20 | 63000 | 3: 3000; 4: 3000; 5: 3000; 6: 3000; 7: 3000; 8: 3000; 9: 3000; 10: 3000; 11: 3000; 12: 3000; 13: 3000; 14: 3000; 15: 3000; 16: 3000; 17: 3000; 18: 3000; 19: 3000; 20: 3000; 21: 3000; 22: 3000; 23: 3000
2.1 | 1 | 1.2 | 3 | 4 | 23 | 24 | 0 | 6000 | 23: 6000
2.2 | 1 | 1.2 | 3 | 4 | 13 | 14 | 10 | 51000 | 6: 51000
3.1 | 5 | 1.3, 2.2 | 7 | 12 | 14 | 19 | 7 | 15000 | 7: 3000; 8: 3000; 9: 3000; 10: 3000; 11: 3000
3.2 | 6 | 1.4 | 19 | 25 | 25 | 31 | 6 | 18000 | 25: 3000; 26: 3000; 27: 3000; 28: 3000; 29: 3000; 30: 3000
3.3 | 3 | 3.1 | 12 | 15 | 21 | 24 | 9 | 9000 | 21: 3000; 22: 3000; 23: 3000
3.4 | 11 | 3.1 | 12 | 23 | 19 | 30 | 7 | 33000 | 12: 3000; 13: 3000; 14: 3000; 15: 3000; 16: 3000; 17: 3000; 18: 3000; 19: 3000; 20: 3000; 21: 3000; 22: 3000
3.5 | 8 | 2.1, 1.5, 3.3 | 24 | 32 | 24 | 32 | 0 | 24000 | 24: 3000; 25: 3000; 26: 3000; 27: 3000; 28: 3000; 29: 3000; 30: 3000; 31: 3000
4.1 | 1 | 3.2 | 25 | 26 | 31 | 32 | 6 | 2000 | 31: 2000
4.2 | 2 | 3.4 | 23 | 25 | 30 | 32 | 7 | 4000 | 30: 2000; 31: 2000
4.3 | 3 | 3.4 | 23 | 26 | 31 | 34 | 8 | 11000 | 31: 3666.6667; 32: 3666.6667; 33: 3666.6667
4.4 | 2 | 3.5, 4.1, 4.2 | 32 | 34 | 32 | 34 | 0 | 4000 | 32: 2000; 33: 2000
[8 empty] | 341000 | 4294.1176 | 4294.1176 | 4294.1176 | 6294.1176 | 6294.1176 | 6294.1176 | 57627.451 | 8627.451 | 8627.451 | 8627.451 | 8627.451 | 8627.451 | 8627.451 | 8627.451 | 8627.451 | 9294.1176 | 9294.1176 | 9294.1176 | 9294.1176 | 9294.1176 | 9294.1176 | 12294.1176 | 12294.1176 | 15294.1176 | 6294.1176 | 8294.1176 | 8294.1176 | 8294.1176 | 8294.1176 | 8294.1176 | 10294.1176 | 12960.7843 | 7960.7843 | 7960.7843 | 0
[9 empty] | 4294.1176 | 8588.2353 | 12882.3529 | 19176.4706 | 25470.5882 | 31764.7059 | 89392.1569 | 98019.6078 | 106647.0588 | 115274.5098 | 123901.9608 | 132529.4118 | 141156.8627 | 149784.3137 | 158411.7647 | 167705.8824 | 177000 | 186294.1176 | 195588.2353 | 204882.3529 | 214176.4706 | 226470.5882 | 238764.7059 | 254058.8235 | 260352.9412 | 268647.0588 | 276941.1765 | 285235.2941 | 293529.4118 | 301823.5294 | 312117.6471 | 325078.4314 | 333039.2157 | 341000
Fatturato |  | 413211.7647
Anticipo | 15% | 61981.7647 |  | 61981.7647
I SAL | 25% | 103302.9412 | Fine 3.1 | 165284.7059
II SAL | 25% | 103302.9412 | Fine 3.4 | 268587.6471
Chiusura | 35% | 144624.1176 |  | 413211.7647
413211.7647

## Risk Analysis
Task | Impatto | Probabilità | Impatto | Contingency reserve | Costo mitigazione | Effetto mitigazione | Contingency reserve con mitigazione | Differenza | Mitigazione? | Budget per risk
1.2 | Aumento durata di 3 settimane | 50% | 10000 | 5000 | 1500 | Nuova probabilità accadimento rischio = 40% | 4000 | 1000 | No | 5000
3.5. | Aumento durata di 3 settimane | 50% | 10000 | 5000 | 4000 | Nuova probabilità accadimento rischio = 0% | 0 | 5000 | Sì | 4000
4.3 | Aumento durata di 1 settimane | 70% | 10000 | 7000 | 4000 | Nuova probabilità accadimento rischio = 20% | 2000 | 5000 | Sì | 6000
15000
penale | 10000

## Piano Risk
[9 empty] | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39
Task | Durata | Predec. | Dmi | Dmf | DMi | DMf | RT | Costo
0.1 | 34 |  | 0 | - | - | - | - | 78000 | 2294.1176 | 2294.1176 | 2294.1176 | 2294.1176 | 2294.1176 | 2294.1176 | 2294.1176 | 2294.1176 | 2294.1176 | 2294.1176 | 2294.1176 | 2294.1176 | 2294.1176 | 2294.1176 | 2294.1176 | 2294.1176 | 2294.1176 | 2294.1176 | 2294.1176 | 2294.1176 | 2294.1176 | 2294.1176 | 2294.1176 | 2294.1176 | 2294.1176 | 2294.1176 | 2294.1176 | 2294.1176 | 2294.1176 | 2294.1176 | 2294.1176 | 2294.1176 | 2294.1176 | 2294.1176
1.1 | 9 | - | 0 | 9 | 6 | 15 | 6 | 3000 | 6: 333.3333; 7: 333.3333; 8: 333.3333; 9: 333.3333; 10: 333.3333; 11: 333.3333; 12: 333.3333; 13: 333.3333; 14: 333.3333
1.2 | 3 | - | 0 | 3 | 0 | 3 | 0 | 8000 | 0: 2666.6667; 1: 2666.6667; 2: 2666.6667
1.3 | 7 | - | 0 | 7 | 7 | 14 | 7 | 7000 | 0: 1000; 1: 1000; 2: 1000; 3: 1000; 4: 1000; 5: 1000; 6: 1000
1.4 | 10 | A | 9 | 19 | 15 | 25 | 6 | 10000 | 15: 1000; 16: 1000; 17: 1000; 18: 1000; 19: 1000; 20: 1000; 21: 1000; 22: 1000; 23: 1000; 24: 1000
1.5 | 21 | B | 3 | 24 | 3 | 24 | 20 | 63000 | 3: 3000; 4: 3000; 5: 3000; 6: 3000; 7: 3000; 8: 3000; 9: 3000; 10: 3000; 11: 3000; 12: 3000; 13: 3000; 14: 3000; 15: 3000; 16: 3000; 17: 3000; 18: 3000; 19: 3000; 20: 3000; 21: 3000; 22: 3000; 23: 3000
2.1 | 1 | B | 3 | 4 | 23 | 24 | 0 | 6000 | 23: 6000
2.2 | 1 | B | 3 | 4 | 13 | 14 | 10 | 51000 | 6: 51000
3.1 | 5 | C,G | 7 | 12 | 14 | 19 | 7 | 15000 | 7: 3000; 8: 3000; 9: 3000; 10: 3000; 11: 3000
3.2 | 6 | D | 19 | 25 | 25 | 31 | 6 | 18000 | 25: 3000; 26: 3000; 27: 3000; 28: 3000; 29: 3000; 30: 3000
3.3 | 3 | H | 12 | 15 | 21 | 24 | 9 | 9000 | 21: 3000; 22: 3000; 23: 3000
3.4 | 11 | H | 12 | 23 | 19 | 30 | 7 | 33000 | 12: 3000; 13: 3000; 14: 3000; 15: 3000; 16: 3000; 17: 3000; 18: 3000; 19: 3000; 20: 3000; 21: 3000; 22: 3000
3.5 | 8 | E,F,L | 24 | 32 | 24 | 32 | 0 | 28000 | 24: 3500; 25: 3500; 26: 3500; 27: 3500; 28: 3500; 29: 3500; 30: 3500; 31: 3500
4.1 | 1 | I | 25 | 26 | 31 | 32 | 6 | 2000 | 31: 2000
4.2 | 2 | M | 23 | 25 | 30 | 32 | 7 | 4000 | 30: 2000; 31: 2000
4.3 | 3 | M | 23 | 26 | 31 | 34 | 8 | 17000 | 23: 5666.6667; 24: 5666.6667; 25: 5666.6667
4.4 | 2 | O,N,P | 32 | 34 | 32 | 34 | 0 | 4000 | 32: 2000; 33: 2000
[8 empty] | 356000 | 5960.7843 | 5960.7843 | 5960.7843 | 6294.1176 | 6294.1176 | 6294.1176 | 57627.451 | 8627.451 | 8627.451 | 8627.451 | 8627.451 | 8627.451 | 8627.451 | 8627.451 | 8627.451 | 9294.1176 | 9294.1176 | 9294.1176 | 9294.1176 | 9294.1176 | 9294.1176 | 12294.1176 | 12294.1176 | 20960.7843 | 12460.7843 | 14460.7843 | 8794.1176 | 8794.1176 | 8794.1176 | 8794.1176 | 10794.1176 | 9794.1176 | 4294.1176 | 4294.1176 | 0
[9 empty] | 5960.7843 | 11921.5686 | 17882.3529 | 24176.4706 | 30470.5882 | 36764.7059 | 94392.1569 | 103019.6078 | 111647.0588 | 120274.5098 | 128901.9608 | 137529.4118 | 146156.8627 | 154784.3137 | 163411.7647 | 172705.8824 | 182000 | 191294.1176 | 200588.2353 | 209882.3529 | 219176.4706 | 231470.5882 | 243764.7059 | 264725.4902 | 277186.2745 | 291647.0588 | 300441.1765 | 309235.2941 | 318029.4118 | 326823.5294 | 337617.6471 | 347411.7647 | 351705.8824 | 356000
Fatturato |  | 413211.7647
Anticipo | 15% | 61981.7647 |  | 61981.7647
I SAL | 25% | 103302.9412 | Fine 3.1 | 165284.7059
II SAL | 25% | 103302.9412 | Fine 3.4 | 268587.6471
Chiusura | 35% | 144624.1176 |  | 413211.7647
413211.7647

## EVM
[9 empty] | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 |  | TN1 (12 settimane) |  |  |  |  | TN2 (24 settimane) |  |  |  |  | Final (34 settimane)
Task | Durata | Predec. | Dmi | Dmf | DMi | DMf | RT | Costo | [35 empty] | Task | Actual | % avan. | EV | CPI | SPI | Actual | % avan. | EV | CPI | SPI | Actual | % avan. | EV | CPI | SPI
0.1 | 34 | - | 0 | - | - | - | - | 78000 | 2294.1176 | 2294.1176 | 2294.1176 | 2294.1176 | 2294.1176 | 2294.1176 | 2294.1176 | 2294.1176 | 2294.1176 | 2294.1176 | 2294.1176 | 2294.1176 | 2294.1176 | 2294.1176 | 2294.1176 | 2294.1176 | 2294.1176 | 2294.1176 | 2294.1176 | 2294.1176 | 2294.1176 | 2294.1176 | 2294.1176 | 2294.1176 | 2294.1176 | 2294.1176 | 2294.1176 | 2294.1176 | 2294.1176 | 2294.1176 | 2294.1176 | 2294.1176 | 2294.1176 | 2294.1176 |  | 0.1 | 26000 | 30% | 23400 | 90% | 85% | 52000 | 60% | 46800 | 90% | 85% | 78000 | 100% | 78000 | 100% | 100%
1.1 | 9 | - | 0 | 9 | 6 | 15 | 6 | 3000 | 6: 333.3333; 7: 333.3333; 8: 333.3333; 9: 333.3333; 10: 333.3333; 11: 333.3333; 12: 333.3333; 13: 333.3333; 14: 333.3333 | 1.1 | 2500 | 80% | 2400 | 96% | 120% | 3200 | 100% | 3000 | 93.75% | 100% | 3200 | 100% | 3000 | 93.75% | 100%
1.2 | 3 | - | 0 | 3 | 0 | 3 | 0 | 8000 | 0: 2666.6667; 1: 2666.6667; 2: 2666.6667 | 1.2 | 7000 | 100% | 8000 | 114.3% | 100% | 7000 | 100% | 8000 | 114.3% | 100% | 7000 | 100% | 8000 | 114.3% | 100%
1.3 | 7 | - | 0 | 7 | 7 | 14 | 7 | 7000 | 0: 1000; 1: 1000; 2: 1000; 3: 1000; 4: 1000; 5: 1000; 6: 1000 | 1.3 | 7500 | 100% | 7000 | 93.33% | 100% | 7500 | 100% | 7000 | 93.33% | 100% | 7500 | 100% | 7000 | 93.33% | 100%
1.4 | 10 | 1.1 | 9 | 19 | 15 | 25 | 6 | 10000 | 15: 1000; 16: 1000; 17: 1000; 18: 1000; 19: 1000; 20: 1000; 21: 1000; 22: 1000; 23: 1000; 24: 1000 | 1.4 | - € | 0% | 0 |  | 0% | 9000 | 95% | 9500 | 105.6% | 105.6% | 10000 | 100% | 10000 | 100% | 100%
1.5 | 21 | 1.2 | 3 | 24 | 3 | 24 | 20 | 63000 |  |  |  | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | [11 empty] | 1.5 | 25000 | 65% | 40950 | 163.8% | 151.7% | 60000 | 100% | 63000 | 105% | 100% | 60000 | 100% | 63000 | 105% | 100%
2.1 | 1 | 1.2 | 3 | 4 | 23 | 24 | 0 | 6000 | 23: 6000 | 2.1 | - € | 0% | 0 |  | 0% | 6000 | 100% | 6000 | 100% | 100% | 6000 | 100% | 6000 | 100% | 100%
2.2 | 1 | 1.2 | 3 | 4 | 13 | 14 | 10 | 51000 | 6: 51000 | 2.2 | 52000 | 100% | 51000 | 98.08% | 100% | 52000 | 100% | 51000 | 98.08% | 100% | 52000 | 100% | 51000 | 98.08% | 100%
3.1 | 5 | 1.3, 2.2 | 7 | 12 | 14 | 19 | 7 | 15000 | 7: 3000; 8: 3000; 9: 3000; 10: 3000; 11: 3000 | 3.1 | 14000 | 95% | 14250 | 101.8% | 95% | 14000 | 100% | 15000 | 107.1% | 100% | 14000 | 100% | 15000 | 107.1% | 100%
3.2 | 6 | 1.4 | 19 | 25 | 25 | 31 | 6 | 18000 | 25: 3000; 26: 3000; 27: 3000; 28: 3000; 29: 3000; 30: 3000 | 3.2 | - € | 0% | 0 |  | 0% | - € | 0% | 0 |  | 0% | 19000 | 100% | 18000 | 94.74% | 100%
3.3 | 3 | 3.1 | 12 | 15 | 21 | 24 | 9 | 9000 | 21: 3000; 22: 3000; 23: 3000 | 3.3 | - € | 0% | 0 |  | 0% | 8500 | 100% | 9000 | 105.9% | 100% | 8500 | 100% | 9000 | 105.9% | 100%
3.4 | 11 | 3.1 | 12 | 23 | 19 | 30 | 7 | 33000 | 12: 3000; 13: 3000; 14: 3000; 15: 3000; 16: 3000; 17: 3000; 18: 3000; 19: 3000; 20: 3000; 21: 3000; 22: 3000 | 3.4 | - € | 0% | 0 |  | 0% | 34000 | 100% | 33000 | 97.06% | 100% | 34000 | 100% | 33000 | 97.06% | 100%
3.5 | 8 | 2.1, 1.5, 3.3 | 24 | 32 | 24 | 32 | 0 | 28000 | 24: 3500; 25: 3500; 26: 3500; 27: 3500; 28: 3500; 29: 3500; 30: 3500; 31: 3500 | 3.5 | - € | 0% | 0 |  | 0% | - € | 0% | 0 |  | 0% | 22000 | 100% | 28000 | 127.3% | 100%
4.1 | 1 | 3.2 | 25 | 26 | 31 | 32 | 6 | 2000 | 31: 2000 | 4.1 | - € | 0% | 0 |  | 0% | - € | 0% | 0 |  | 0% | 2000 | 100% | 2000 | 100% | 100%
4.2 | 2 | 3.4 | 23 | 25 | 30 | 32 | 7 | 4000 | 30: 2000; 31: 2000 | 4.2 | - € | 0% | 0 |  | 0% | - € | 0% | 0 |  | 0% | 4000 | 100% | 4000 | 100% | 100%
4.3 | 3 | 3.4 | 23 | 26 | 31 | 34 | 8 | 17000 | 23: 5666.6667; 24: 5666.6667; 25: 5666.6667 | 4.3 | - € | 0% | 0 |  | 0% | - € | 0% | 0 |  | 0% | 10500 | 100% | 17000 | 161.9% | 100%
4.4 | 2 | 3.5, 4.1, 4.2 | 32 | 34 | 32 | 34 | 0 | 4000 | 32: 2000; 33: 2000 | 4.4 | - € | 0% | 0 |  | 0% | - € | 0% | 0 |  | 0% | 6000 | 100% | 4000 | 66.67% | 100%
[8 empty] | 356000 | 5960.7843 | 5960.7843 | 5960.7843 | 6294.1176 | 6294.1176 | 6294.1176 | 57627.451 | 8627.451 | 8627.451 | 8627.451 | 8627.451 | 8627.451 | 8627.451 | 8627.451 | 8627.451 | 9294.1176 | 9294.1176 | 9294.1176 | 9294.1176 | 9294.1176 | 9294.1176 | 12294.1176 | 12294.1176 | 20960.7843 | 12460.7843 | 14460.7843 | 8794.1176 | 8794.1176 | 8794.1176 | 8794.1176 | 10794.1176 | 9794.1176 | 4294.1176 | 4294.1176 |  |  | 134000 |  | 147000 | 109.7% | 106.9% | 253200 |  | 251300 | 99.25% | 94.93% | 343700 |  | 356000 | 103.6% | 100%
[8 empty] | PV | 5960.7843 | 11921.5686 | 17882.3529 | 24176.4706 | 30470.5882 | 36764.7059 | 94392.1569 | 103019.6078 | 111647.0588 | 120274.5098 | 128901.9608 | 137529.4118 | 146156.8627 | 154784.3137 | 163411.7647 | 172705.8824 | 182000 | 191294.1176 | 200588.2353 | 209882.3529 | 219176.4706 | 231470.5882 | 243764.7059 | 264725.4902 | 277186.2745 | 291647.0588 | 300441.1765 | 309235.2941 | 318029.4118 | 326823.5294 | 337617.6471 | 347411.7647 | 351705.8824 | 356000
Fatturato |  | 413211.7647 | [42 empty] | EAC | 312242.8019 |  |  |  | EAC | 364327.4035 |  |  |  | EAC | 343700
Anticip | 15% | 61981.7647 |  | 61981.7647
I SAL | 25% | 103302.9412 | Fine H | 165284.7059
II SAL | 25% | 103302.9412 | Fine M | 268587.6471
Chiusura | 35% | 144624.1176 |  | 413211.7647
413211.7647
AC
PV
EV

## Dashboard
SPI
|  | < | 1 | >
>
CPI | 1
>
0.1
1.1
1.2
1.3
1.5
Proj
3.1
2.2